## general_report
SEF Jira
Displaying 131 issues at 25/Oct/16 12:47 PM.
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Resolved | Affects Version/s | Fix Version/s | Component/s | Due Date | Votes | Watchers | Images | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Sub-Tasks | Linked Issues | Environment | Description | Security Level | Progress | Σ Progress | Σ Time Spent | Σ Remaining Estimate | Σ Original Estimate | Labels | Epic Link | Epic/Theme | Flagged | Rank | Sprint
IFB299 2016-Sem2 055 | AALV-200 | Teacher - Cancel lesson | Story | Closed | Major | Fixed | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-10-18 10:11 | 2016-10-18 12:25 | 2016-10-23 13:15 | 2016-10-23 13:15 |  |  |  |  | 0 | 2 |  |  | 1800 | 0 |  | AALV-203, AALV-204 | AALV-51 |  | As a teacher, I want to cancel a lesson so that I do not have to attend. * Future lessons listed * Able to Cancel selected lesson(s) * Email confirmation sent to student and teacher |  | 0% | 66% | 14400 | 7200 | 21600 |  |  |  |  | 0¦ywnw26: | Sprint 4
IFB299 2016-Sem2 055 | AALV-199 | Test Other Issues | Task | Open | Critical | Unresolved | Brenton Buchbach | Richard Van Wyk | Richard Van Wyk | 2016-10-11 14:30 | 2016-10-11 14:30 | 2016-10-17 20:06 | [5 empty] | 0 | 1 |  | 7200 | 5820 | 1380 | 19% | [5 empty] | 19% | 19% | 1380 | 5820 | 7200 |  |  |  |  | 0¦0000gl:4 | Sprint 4
IFB299 2016-Sem2 055 | AALV-198 | Improve View Student Applications | Improvement | Closed | Minor | Fixed | Brendan Rothwell | Richard Van Wyk | Richard Van Wyk | 2016-10-10 11:53 | 2016-10-20 10:23 | 2016-10-25 00:12 | 2016-10-25 00:12 |  |  |  |  | 0 | 1 |  | 10800 | 3600 | 7200 | 66% |  |  |  | Individual: Change Back button to be blue. Reorder fields (Year, term, start, end) Default Notes to N/A if no value given All: Remove age Add "start - end" time Add indicator if they've requested that teacher specifically |  | 66% | 66% | 7200 | 3600 | 10800 |  |  |  |  | 0¦0000gl:9 | Sprint 4
IFB299 2016-Sem2 055 | AALV-197 | Add another lesson length (30m) | Improvement | In Progress | Major | Unresolved | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-10-10 10:00 | 2016-10-22 17:30 | 2016-10-22 17:30 | [5 empty] | 0 | 2 |  | 10800 | 3600 | 7200 | 66% |  |  |  | A lesson length needs to be added to the lesson application page. This will involve adding it to front end and adding a calculation for end time. Don't think it requires node changes but might. |  | 66% | 66% | 7200 | 3600 | 10800 |  |  |  |  | 0¦0000gl:i | Sprint 4
IFB299 2016-Sem2 055 | AALV-196 | Add language and instrument skills to teacher registration | Improvement | Resolved | Major | Done | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-10-10 09:58 | 2016-10-18 17:31 | 2016-10-11 14:29 | 2016-10-11 14:29 |  |  |  |  | 0 | 1 |  | 14400 | 0 | 10800 | 75% | [5 empty] | 100% | 100% | 10800 | 0 | 14400 |  |  |  |  | 0¦ywnuou: | Sprint 3
IFB299 2016-Sem2 055 | AALV-195 | Add gender to students, teachers, managers and teacher applicants | Improvement | Resolved | Major | Fixed | Brendan Rothwell | Richard Van Wyk | Richard Van Wyk | 2016-10-10 09:58 | 2016-10-10 09:58 | 2016-10-25 00:08 | 2016-10-25 00:08 |  |  |  |  | 0 | 1 |  | 18000 | 18000 |  | 0% |  |  |  | Add Gender to the three accounts. Add to DB Add to Angular Apps Add to Node back end |  | 0% | 0% |  | 18000 | 18000 |  |  |  |  | 0¦0000gm: | Sprint 4
IFB299 2016-Sem2 055 | AALV-194 | Add account validation to Accept Student Applications | Improvement | Closed | Major | Fixed | Aditya Raja | Richard Van Wyk | Richard Van Wyk | 2016-10-10 09:56 | 2016-10-10 16:25 | 2016-10-18 15:45 | 2016-10-18 15:45 |  |  |  |  | 0 | 2 |  | 3600 | 3600 | 3600 | 100% |  |  |  | The accept student application page needs to have an extra restriction so that only teachers can view the page. |  | 50% | 50% | 3600 | 3600 | 3600 |  |  |  |  | 0¦0000gl: | Sprint 4
IFB299 2016-Sem2 055 | AALV-193 | Fix Date Validation on all registration Forms | Improvement | Resolved | Major | Fixed | Brendan Rothwell | Richard Van Wyk | Richard Van Wyk | 2016-10-10 09:53 | 2016-10-10 09:53 | 2016-10-25 00:08 | 2016-10-25 00:08 |  |  |  |  | 0 | 1 |  | 10800 | 10800 |  | 0% |  |  |  | Fix the Validation - Look into Jquery Datepicker to handle that. |  | 0% | 0% |  | 10800 | 10800 |  |  |  |  | 0¦0000gn: | Sprint 4
IFB299 2016-Sem2 055 | AALV-149 | Feature Emailing | Bug | Resolved | Major | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-09-19 12:34 | 2016-09-21 21:47 | 2016-09-21 21:47 | 2016-09-21 21:47 | V1 | V1 |  |  | 0 | 1 |  | 7200 | 0 | 10800 | 150% |  |  |  | Not all features that require emailing have it implemented. |  | 100% | 100% | 10800 | 0 | 7200 |  |  |  |  | 0¦ywnpvu: | Sprint 2
IFB299 2016-Sem2 055 | AALV-148 | User - Login | Story | Resolved | Critical | Fixed | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-09-16 20:16 |  | 2016-09-19 16:34 | 2016-09-18 17:46 | V1 | V1 |  |  | 0 | 1 |  | 14400 | 0 | 14400 | 100% |  |  |  | As a user, I want to log in to the site so that I can use its services. |  | 100% | 100% | 14400 | 0 | 14400 |  |  |  |  | 0¦ywnphq: | Sprint 2
IFB299 2016-Sem2 055 | AALV-146 | Student - View Lesson Applications | Story | Closed | Major | Duplicate | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-09-15 11:10 |  | 2016-10-06 15:09 | 2016-10-06 15:09 |  |  |  |  | 0 | 1 | [8 empty] | As a student, I want to view my lesson applications or be notified of them so that I know if they've been rejected. | [10 empty] | 0¦ywn62m:i
IFB299 2016-Sem2 055 | AALV-145 | AALV-29 Test Instruments History page | Sub-task | Resolved | Major | Fixed | Brenton Buchbach | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:44 | 2016-09-21 21:47 | 2016-09-21 21:47 | 2016-09-21 21:47 |  |  |  |  | 0 | 1 |  | 7200 | 5100 | 2100 | 29% | [5 empty] | 29% | 29% | 2100 | 5100 | 7200 |  |  |  |  | 0¦ywnluu: | Sprint 2
IFB299 2016-Sem2 055 | AALV-144 | AALV-29 Create AngularJS and Node.JS apps | Sub-task | Closed | Major | Fixed | Anneke Kotze | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:43 |  | 2016-09-18 16:29 | 2016-09-18 16:20 |  |  |  |  | 0 | 2 |  | 14400 | 9000 | 5400 | 37% |  |  |  | Get Teachers, Fill with teachers. When button is clicked, bring up confirmation. On confirmation, delete. If not manager, redirect to home page. |  | 37% | 37% | 5400 | 9000 | 14400 |  |  |  |  | 0¦ywnlum: | Sprint 2
IFB299 2016-Sem2 055 | AALV-143 | AALV-29 Create Teacher Deactivation Page | Sub-task | Resolved | Major | Fixed | Anneke Kotze | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:41 |  | 2016-09-18 20:45 | 2016-09-18 20:45 |  |  |  |  | 0 | 1 |  | 14400 | 0 | 21600 | 150% |  |  |  | Make manager registration form in the website/deactivateTeachers/views/ folder in ejs file with "form" in the name. Ensure no inline css, add css to website/deactivateTeachers/css/ folder in css file corresponding to the ejs file (should have same name). Should be a table, listing significant teacher info with button at the end to "Deactivate". Should have a filter at the top. (Don't worry about functionality, just need a good looking text field that can be typed into) |  | 100% | 100% | 21600 | 0 | 14400 |  |  |  |  | 0¦ywnlue: | Sprint 2
IFB299 2016-Sem2 055 | AALV-142 | AALV-29 Create Folder Structure | Sub-task | Closed | Critical | Fixed | Anneke Kotze | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:38 |  | 2016-09-10 16:08 | 2016-09-10 16:08 |  |  |  |  | 0 | 1 |  | 1800 | 0 | 1800 | 100% |  |  |  | Create folder structure /management/teachers/deactivate/ ensure css is correctly linked. |  | 100% | 100% | 1800 | 0 | 1800 |  |  |  |  | 0¦ywnlu6: | Sprint 2
IFB299 2016-Sem2 055 | AALV-141 | AALV-58 Create Folder Structure | Sub-task | Resolved | Critical | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:36 |  | 2016-09-10 11:22 | 2016-09-10 11:22 |  |  |  |  | 0 | 1 |  |  | 0 | 3600 |  |  |  |  | Create folder structure /information/ ensure css is correctly linked. |  | 100% | 100% | 3600 | 0 | [5 empty] | 0¦ywnlty: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-140 | AALV-32 Create Folder Structure | Sub-task | Closed | Critical | Fixed | Anneke Kotze | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:34 |  | 2016-09-10 15:22 | 2016-09-10 15:22 |  |  |  |  | 0 | 1 |  | 1800 | 0 | 1800 | 100% |  |  |  | Create folder structure /management/instrument/requests/ ensure css is correctly linked. |  | 100% | 100% | 1800 | 0 | 1800 |  |  |  |  | 0¦ywnltq: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-139 | AALV-35 Create Folder Structure | Sub-task | Closed | Critical | Fixed | Anneke Kotze | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:32 |  | 2016-09-10 14:37 | 2016-09-10 14:37 |  |  |  |  | 0 | 1 |  | 1800 | 0 | 1800 | 100% |  |  |  | Create folder structure /management/instruments/return/ ensure css is correctly linked. |  | 100% | 100% | 1800 | 0 | 1800 |  |  |  |  | 0¦ywnlti: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-138 | AALV-61 Create Folder Structure | Sub-task | Closed | Critical | Fixed | Anneke Kotze | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:31 |  | 2016-09-10 14:05 | 2016-09-10 14:05 |  |  |  |  | 0 | 1 |  | 1800 | 0 | 3600 | 200% |  |  |  | Create folder structure /teacher/studentApplications/ ensure css is correctly linked. |  | 100% | 100% | 3600 | 0 | 1800 |  |  |  |  | 0¦ywnlta: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-137 | AALV-15 Test Instruments History page | Sub-task | Resolved | Major | Fixed | Brenton Buchbach | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:28 | 2016-09-21 21:47 | 2016-09-21 21:47 | 2016-09-21 21:47 |  |  |  |  | 0 | 1 |  | 7200 | 6000 | 1200 | 16% | [5 empty] | 16% | 16% | 1200 | 6000 | 7200 |  |  |  |  | 0¦ywnlt2: | Sprint 2
IFB299 2016-Sem2 055 | AALV-136 | AALV-15 Create AngularJS and Node.JS apps | Sub-task | Resolved | Major | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:28 | 2016-09-19 16:20 | 2016-09-19 16:20 | 2016-09-19 16:20 |  |  |  |  | 0 | 2 |  | 10800 | 0 | 9000 | 83% |  |  |  | Fetch instrument history, display. display message if none. display error if not logged in. |  | 100% | 100% | 9000 | 0 | 10800 |  |  |  |  | 0¦ywnlsu: | Sprint 2
IFB299 2016-Sem2 055 | AALV-135 | AALV-15 Create Instrument History Page | Sub-task | Closed | Major | Done | Bhupinder Singh Saini | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:27 |  | 2016-09-18 19:47 | 2016-09-18 19:47 |  |  |  |  | 0 | 1 |  | 14400 | 14400 |  | 0% |  |  |  | Make manager registration form in the website/instrumentHistory/views/ folder in ejs file with "form" in the name. Ensure no inline css, add css to website/instrumentHistory/css/ folder in css file corresponding to the ejs file (should have same name). Should be table form. See Acceptance testing or ERD for columns |  | 0% | 0% |  | 14400 | 14400 |  |  |  |  | 0¦ywnlsm: | Sprint 2
IFB299 2016-Sem2 055 | AALV-134 | AALV-15 Create Folder Structure | Sub-task | Resolved | Major | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:25 |  | 2016-09-10 14:37 | 2016-09-10 14:37 |  |  |  |  | 0 | 1 |  | 1800 | 0 | 1800 | 100% |  |  |  | Create folder structure /student/instruments/history/ ensure css is correctly linked. |  | 100% | 100% | 1800 | 0 | 1800 |  |  |  |  | 0¦ywnlse: | Sprint 2
IFB299 2016-Sem2 055 | AALV-133 | AALV-59 Test Borrowed Instruments page | Sub-task | Resolved | Major | Fixed | Brenton Buchbach | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:21 | 2016-09-21 21:46 | 2016-09-21 21:46 | 2016-09-21 21:46 |  |  |  |  | 0 | 1 |  | 7200 | 5220 | 1980 | 27% |  |  |  | See Acceptance Criteria, ensure it is met and that everything logically works. Ensure no fields missing that should be there. |  | 27% | 27% | 1980 | 5220 | 7200 |  |  |  |  | 0¦ywnls6: | Sprint 2
IFB299 2016-Sem2 055 | AALV-132 | AALV-59 Create AngularJS and Node.JS apps | Sub-task | Closed | Major | Fixed | Anneke Kotze | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:21 |  | 2016-09-18 17:12 | 2016-09-18 17:12 |  |  |  |  | 0 | 1 |  | 10800 | 5400 | 5400 | 50% |  |  |  | Link to DB, pull all instruments for logged in student, display. If not logged in, give error. If no instruments, give message. |  | 50% | 50% | 5400 | 5400 | 10800 |  |  |  |  | 0¦ywnlry: | Sprint 2
IFB299 2016-Sem2 055 | AALV-131 | AALV-59 Create Instrument Information Page | Sub-task | Resolved | Major | Fixed | Sara Abdulrahman M Alraddadi | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:20 |  | 2016-09-11 19:36 | 2016-09-11 19:36 |  |  |  |  | 0 | 1 |  | 14400 | 3600 | 10800 | 75% |  |  |  | Create page that lists the information on the instruments that a specific student has borrowed. "card" format instead of a table (ask me if you don't know what I mean by that) |  | 75% | 75% | 10800 | 3600 | 14400 |  |  |  |  | 0¦ywnlrq: | Sprint 2
IFB299 2016-Sem2 055 | AALV-130 | AALV-59 Create Folder Structure | Sub-task | Resolved | Major | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:18 |  | 2016-09-10 14:05 | 2016-09-10 14:05 |  |  |  |  | 0 | 1 |  | 1800 | 0 | 1800 | 100% |  |  |  | Create folder structure /student/instruments/borrowed/ ensure css is correctly linked. |  | 100% | 100% | 1800 | 0 | 1800 |  |  |  |  | 0¦ywnlri: | Sprint 2
IFB299 2016-Sem2 055 | AALV-129 | AALV-119 Test Manager registration and Login | Sub-task | Resolved | Major | Fixed | Brenton Buchbach | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:13 | 2016-09-21 21:44 | 2016-09-21 21:44 | 2016-09-21 21:44 |  |  |  |  | 0 | 1 |  | 7200 | 0 | 3600 | 50% |  |  |  | See Acceptance Criteria, ensure it is met and that everything logically works. Ensure no fields missing that should be there. |  | 100% | 100% | 3600 | 0 | 7200 |  |  |  |  | 0¦ywnlqu: | Sprint 2
IFB299 2016-Sem2 055 | AALV-128 | AALV-119 Link existing loginService to new Login Form | Sub-task | Resolved | Major | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:13 | 2016-09-18 21:23 | 2016-09-18 21:23 | 2016-09-18 21:23 |  |  |  |  | 0 | 1 |  | 14400 | 0 | 7200 | 50% |  |  |  | Ensure code isn't being duplicated in terms of services etc. |  | 100% | 100% | 7200 | 0 | 14400 |  |  |  |  | 0¦ywnlqm: | Sprint 2
IFB299 2016-Sem2 055 | AALV-127 | AALV-119 Create Manager Login Form | Sub-task | Resolved | Major | Fixed | Aditya Raja | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:12 | 2016-09-21 21:44 | 2016-09-21 21:44 | 2016-09-21 21:44 |  |  |  |  | 0 | 2 |  | 7200 | 0 | 3690 | 51% |  |  |  | Make manager login form in the website/managerLogin/views/ folder in ejs file with "form" in the name. Ensure no inline css, add css to website/managerLogin/css/ folder in css file corresponding to the ejs file (should have same name). Should have email and password fields. |  | 100% | 100% | 3690 | 0 | 7200 |  |  |  |  | 0¦ywnlq6: | Sprint 2
IFB299 2016-Sem2 055 | AALV-126 | AALV-119 Create AngularJS and Node.JS apps | Sub-task | Resolved | Major | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:11 | 2016-09-19 12:33 | 2016-09-19 12:33 | 2016-09-19 12:33 |  |  |  |  | 0 | 1 |  | 10800 | 0 | 7200 | 66% |  |  |  | Follow studentRegistration Structure |  | 100% | 100% | 7200 | 0 | 10800 |  |  |  |  | 0¦ywnlpi: | Sprint 2
IFB299 2016-Sem2 055 | AALV-125 | AALV-119 Create Manager Registration Form | Sub-task | Resolved | Major | Fixed | Bhupinder Singh Saini | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:10 |  | 2016-09-18 15:51 | 2016-09-18 15:51 |  |  |  |  | 0 | 1 |  | 14400 | 14280 | 120 | 0% |  |  |  | Make manager registration form in the website/registerManager/views/ folder in ejs file with "form" in the name. Ensure no inline css, add css to website/registerManager/css/ folder in css file corresponding to the ejs file (should have same name). See acceptance criteria or ERD for fields. |  | 0% | 0% | 120 | 14280 | 14400 |  |  |  |  | 0¦ywnlpa: | Sprint 2
IFB299 2016-Sem2 055 | AALV-124 | AALV-119 Create Folder Structure | Sub-task | Resolved | Major | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:07 |  | 2016-09-10 13:11 | 2016-09-10 13:11 |  |  |  |  | 0 | 1 |  | 1800 | 0 | 1800 | 100% |  |  |  | Create folder structure for registerManager |  | 100% | 100% | 1800 | 0 | 1800 |  |  |  |  | 0¦ywnlou: | Sprint 2
IFB299 2016-Sem2 055 | AALV-123 | AALV-58 Create Services for instrument getting | Sub-task | Closed | Critical | Fixed | Anneke Kotze | Richard Van Wyk | Richard Van Wyk | 2016-09-08 12:00 |  | 2016-09-16 16:51 | 2016-09-16 16:51 |  |  |  |  | 0 | 1 |  | 7200 | 3600 | 3600 | 50% |  |  |  | the instrument list and the table should be filled by the DB. |  | 50% | 50% | 3600 | 3600 | 7200 |  |  |  |  | 0¦ywnlny: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-122 | AALV-12 Send Confirmation | Sub-task | Closed | Major | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-09-08 11:56 | 2016-10-10 16:23 | 2016-10-10 16:23 | 2016-10-10 16:23 |  |  |  |  | 0 | 1 |  | 7200 | 0 | 7200 | 100% |  |  |  | Email student and Teacher about lesson booking |  | 100% | 100% | 7200 | 0 | 7200 |  |  |  |  | 0¦ywnlna: | Sprint 1, Sprint 3
IFB299 2016-Sem2 055 | AALV-121 | AALV-61 Send Confirmation | Sub-task | Resolved | Major | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-09-08 11:39 | 2016-09-18 21:40 | 2016-09-18 21:40 | 2016-09-18 21:40 |  |  |  |  | 0 | 1 |  | 10800 | 0 | 7200 | 66% |  |  |  | Send Email confirmation to students confirming their registration. |  | 100% | 100% | 7200 | 0 | 10800 |  |  |  |  | 0¦ywnllq: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-119 | Owner - Register Managers | Story | Resolved | Must Have | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-09-08 11:34 | 2016-09-21 21:44 | 2016-09-21 21:44 | 2016-09-21 21:44 | V1 | V1 |  |  | 0 | 1 | [5 empty] | AALV-124, AALV-125, AALV-126, AALV-127, AALV-128, AALV-129 |  |  | As the owner, I would like to register managers so that they can manage my business. |  |  | 62% | 23610 | 14280 | 55800 |  |  |  |  | 0¦0000lp:i | Sprint 2
IFB299 2016-Sem2 055 | AALV-118 | AALV-58 Style Page | Sub-task | Resolved | Major | Fixed | Sara Abdulrahman M Alraddadi | Richard Van Wyk | Richard Van Wyk | 2016-09-08 11:30 |  | 2016-09-11 16:06 | 2016-09-11 16:06 |  |  |  |  | 0 | 1 |  | 7200 | 0 | 14400 | 200% | [5 empty] | 100% | 100% | 14400 | 0 | 7200 |  |  |  |  | 0¦ywnlli: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-117 | AALV-12 Test request specific teacher | Sub-task | Closed | Major | Fixed | Brenton Buchbach | Richard Van Wyk | Richard Van Wyk | 2016-08-27 14:07 |  | 2016-10-16 17:10 | 2016-10-16 17:10 |  |  |  |  | 0 | 1 |  | 7200 | 6300 | 900 | 12% | [5 empty] | 12% | 12% | 900 | 6300 | 7200 |  |  |  |  | 0¦ywnin3: | Sprint 1, Sprint 3
IFB299 2016-Sem2 055 | AALV-115 | AALV-12 Create Service(s) for Processing Data | Sub-task | Resolved | Major | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-08-27 14:06 | 2016-10-10 12:04 | 2016-10-10 12:04 | 2016-10-10 12:04 |  |  |  |  | 0 | 1 |  | 14400 | 0 | 14400 | 100% | [5 empty] | 100% | 100% | 14400 | 0 | 14400 |  |  |  |  | 0¦ywnimn: | Sprint 1, Sprint 3
IFB299 2016-Sem2 055 | AALV-114 | AALV-12 Create Request Teacher Form Page | Sub-task | Closed | Major | Fixed | Sara Abdulrahman M Alraddadi | Richard Van Wyk | Richard Van Wyk | 2016-08-27 14:06 |  | 2016-09-30 14:24 | 2016-09-15 23:10 |  |  |  |  | 0 | 1 |  | 14400 | 0 | 23400 | 162% | [5 empty] | 100% | 100% | 23400 | 0 | 14400 |  |  |  |  | 0¦ywnimf: | Sprint 1, Sprint 3
IFB299 2016-Sem2 055 | AALV-113 | AALV-12 Create DB table(s) and Queries | Sub-task | Closed | Major | Fixed | Brendan Rothwell | Richard Van Wyk | Richard Van Wyk | 2016-08-27 14:06 |  | 2016-09-04 17:41 | 2016-09-04 17:41 |  |  |  |  | 0 | 1 |  | 7200 | 7140 | 60 | 0% | [5 empty] | 0% | 0% | 60 | 7140 | 7200 |  |  |  |  | 0¦ywnim7: | Sprint 1, Sprint 3
IFB299 2016-Sem2 055 | AALV-112 | AALV-32 Test Hire Request View | Sub-task | Resolved | Major | Fixed | Brenton Buchbach | Richard Van Wyk | Richard Van Wyk | 2016-08-27 14:05 | 2016-09-21 21:45 | 2016-09-21 21:45 | 2016-09-21 21:45 |  |  |  |  | 0 | 1 |  | 7200 | 0 | 5100 | 70% | [5 empty] | 100% | 100% | 5100 | 0 | 7200 |  |  |  |  | 0¦ywnilz: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-111 | AALV-32 Create Service(s) for processing/generating data | Sub-task | Resolved | Major | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-08-27 14:05 | 2016-09-19 16:20 | 2016-09-19 16:20 | 2016-09-19 16:20 |  |  |  |  | 0 | 2 |  | 18000 | 0 | 10800 | 60% | [5 empty] | 100% | 100% | 10800 | 0 | 18000 |  |  |  |  | 0¦ywnilr: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-110 | AALV-32 Create Hire Request View Page | Sub-task | Resolved | Major | Fixed | Bhupinder Singh Saini | Richard Van Wyk | Richard Van Wyk | 2016-08-27 14:05 |  | 2016-09-18 17:30 | 2016-09-18 17:30 |  |  |  |  | 0 | 1 |  | 14400 | 14310 | 90 | 0% |  |  |  | Create a fieldset and add it to the existing Lesson Application form. |  | 0% | 0% | 90 | 14310 | 14400 |  |  |  |  | 0¦ywnilj: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-109 | AALV-32 Create DB Queries | Sub-task | Closed | Major | Fixed | Brendan Rothwell | Richard Van Wyk | Richard Van Wyk | 2016-08-27 14:05 |  | 2016-09-04 17:41 | 2016-09-04 17:41 |  |  |  |  | 0 | 1 |  | 3600 | 3540 | 60 | 1% | [5 empty] | 1% | 1% | 60 | 3540 | 3600 |  |  |  |  | 0¦ywnilb: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-108 | AALV-35 Test Return Page | Sub-task | Resolved | Major | Fixed | Brenton Buchbach | Richard Van Wyk | Richard Van Wyk | 2016-08-27 14:03 | 2016-09-21 21:44 | 2016-09-21 21:44 | 2016-09-21 21:44 |  |  |  |  | 0 | 1 |  |  | 0 | 4680 | [6 empty] | 100% | 100% | 4680 | 0 | [5 empty] | 0¦ywnil3: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-107 | AALV-35 Create Service(s) for processing/generating data | Sub-task | Closed | Major | Fixed | Anneke Kotze | Richard Van Wyk | Richard Van Wyk | 2016-08-27 14:03 |  | 2016-09-16 19:52 | 2016-09-16 19:52 |  |  |  |  | 0 | 1 |  | 14400 | 5400 | 9000 | 62% | [5 empty] | 62% | 62% | 9000 | 5400 | 14400 |  |  |  |  | 0¦ywnikv: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-106 | AALV-35 Create Instrument Return Page | Sub-task | Closed | Major | Fixed | Anneke Kotze | Richard Van Wyk | Richard Van Wyk | 2016-08-27 14:03 |  | 2016-09-18 21:11 | 2016-09-18 21:11 |  |  |  |  | 0 | 1 |  | 10800 | 0 | 19200 | 177% | [5 empty] | 100% | 100% | 19200 | 0 | 10800 |  |  |  |  | 0¦ywnikn: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-105 | AALV-35 Create DB Queries | Sub-task | Closed | Major | Fixed | Brendan Rothwell | Richard Van Wyk | Richard Van Wyk | 2016-08-27 14:02 |  | 2016-09-10 14:37 | 2016-09-08 11:13 |  |  |  |  | 0 | 1 |  | 3600 | 0 | 3600 | 100% | [5 empty] | 100% | 100% | 3600 | 0 | 3600 |  |  |  |  | 0¦ywnikf: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-104 | AALV-14 Testing of Instrument Hire | Sub-task | Resolved | Major | Fixed | Brenton Buchbach | Richard Van Wyk | Richard Van Wyk | 2016-08-27 14:02 | 2016-09-21 21:44 | 2016-09-21 21:44 | 2016-09-21 21:44 |  |  |  |  | 0 | 1 |  | 7200 | 0 | 5700 | 79% | [5 empty] | 100% | 100% | 5700 | 0 | 7200 |  |  |  |  | 0¦ywnik7: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-103 | AALV-14 Create Confirmation Page & Send Notification | Sub-task | Resolved | Major | Fixed | Sara Abdulrahman M Alraddadi | Richard Van Wyk | Richard Van Wyk | 2016-08-27 14:02 |  | 2016-09-08 11:12 | 2016-09-08 02:28 |  |  |  |  | 0 | 1 |  | 7200 | 0 | 3600 | 50% | [5 empty] | 100% | 100% | 3600 | 0 | 7200 |  |  |  |  | 0¦ywnijz: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-102 | AALV-14 Create Service(s) for Processing Data | Sub-task | Resolved | Major | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-08-27 14:01 |  | 2016-09-18 17:47 | 2016-09-16 20:12 |  |  |  |  | 0 | 1 |  | 14400 | 0 | 28860 | 200% | [5 empty] | 100% | 100% | 28860 | 0 | 14400 |  |  |  |  | 0¦ywnijr: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-101 | AALV-14 Create Search Form Page | Sub-task | Closed | Major | Fixed | Bhupinder Singh Saini | Richard Van Wyk | Richard Van Wyk | 2016-08-27 14:01 | 2016-09-18 19:50 | 2016-09-18 19:50 | 2016-09-18 19:50 |  |  |  |  | 0 | 1 |  | 21600 | 10800 | 10800 | 50% | [5 empty] | 50% | 50% | 10800 | 10800 | 21600 |  |  |  |  | 0¦ywnijj: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-100 | AALV-14 Create DB table(s) and Queries | Sub-task | Closed | Major | Fixed | Brendan Rothwell | Richard Van Wyk | Richard Van Wyk | 2016-08-27 14:00 |  | 2016-09-04 17:39 | 2016-09-04 17:39 |  |  |  |  | 0 | 1 |  | 7200 | 0 | 7260 | 100% | [5 empty] | 100% | 100% | 7260 | 0 | 7200 |  |  |  |  | 0¦ywnijb: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-99 | AALV-37 Test add new instrument function | Sub-task | Closed | Major | Incomplete | Brenton Buchbach | Richard Van Wyk | Richard Van Wyk | 2016-08-27 12:13 |  | 2016-09-08 00:22 | 2016-09-08 00:22 |  |  |  |  | 0 | 1 |  | 7200 | 7200 |  | 0% | [5 empty] | 0% | 0% |  | 7200 | 7200 |  |  |  |  | 0¦ywnij3: | Sprint 1
IFB299 2016-Sem2 055 | AALV-98 | AALV-37 Create service(s) for processing data | Sub-task | Resolved | Major | Fixed | Anneke Kotze | Richard Van Wyk | Richard Van Wyk | 2016-08-27 12:12 |  | 2016-09-08 11:11 | 2016-09-08 11:11 |  |  |  |  | 0 | 1 |  | 10800 | 0 | 7200 | 66% | [5 empty] | 100% | 100% | 7200 | 0 | 10800 |  |  |  |  | 0¦ywniiv: | Sprint 1
IFB299 2016-Sem2 055 | AALV-97 | AALV-37 Add Instrument form validation | Sub-task | Closed | Major | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-08-27 12:11 |  | 2016-09-08 00:21 | 2016-09-08 00:21 |  |  |  |  | 0 | 1 |  | 7200 | 0 | 7200 | 100% | [5 empty] | 100% | 100% | 7200 | 0 | 7200 |  |  |  |  | 0¦ywniin: | Sprint 1
IFB299 2016-Sem2 055 | AALV-96 | AALV-37 Create instrument addition form page | Sub-task | Resolved | Major | Fixed | Sara Abdulrahman M Alraddadi | Richard Van Wyk | Richard Van Wyk | 2016-08-27 12:11 |  | 2016-09-08 11:10 | 2016-09-02 17:07 |  |  |  |  | 0 | 1 |  | 10800 | 0 | 7200 | 66% | [5 empty] | 100% | 100% | 7200 | 0 | 10800 |  |  |  |  | 0¦ywniif: | Sprint 1
IFB299 2016-Sem2 055 | AALV-95 | AALV-37 Create DB table(s) and Queries | Sub-task | Closed | Major | Fixed | Brendan Rothwell | Richard Van Wyk | Richard Van Wyk | 2016-08-27 12:11 |  | 2016-09-04 17:38 | 2016-09-04 17:38 |  |  |  |  | 0 | 1 |  | 7200 | 0 | 7260 | 100% | [5 empty] | 100% | 100% | 7260 | 0 | 7200 |  |  |  |  | 0¦ywnii7: | Sprint 1
IFB299 2016-Sem2 055 | AALV-94 | AALV-58 Test student lesson view | Sub-task | Closed | Major | Done | Brenton Buchbach | Richard Van Wyk | Richard Van Wyk | 2016-08-27 12:09 |  | 2016-09-19 13:40 | 2016-09-19 13:40 |  |  |  |  | 0 | 1 |  | 7200 | 6780 | 420 | 5% | [5 empty] | 5% | 5% | 420 | 6780 | 7200 |  |  |  |  | 0¦ywnihn: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-90 | AALV-58 Create DB tables(s) and Queries | Sub-task | Closed | Major | Fixed | Brendan Rothwell | Richard Van Wyk | Richard Van Wyk | 2016-08-27 12:08 |  | 2016-09-04 17:36 | 2016-09-04 17:36 |  |  |  |  | 0 | 1 |  | 7200 | 0 | 7200 | 100% | [5 empty] | 100% | 100% | 7200 | 0 | 7200 |  |  |  |  | 0¦ywnih3: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-89 | AALV-61 Test accepting students | Sub-task | Resolved | Major | Fixed | Brenton Buchbach | Richard Van Wyk | Richard Van Wyk | 2016-08-27 12:07 | 2016-09-21 21:43 | 2016-09-21 21:43 | 2016-09-21 21:43 |  |  |  |  | 0 | 1 |  | 7200 | 0 | 3600 | 50% | [5 empty] | 100% | 100% | 3600 | 0 | 7200 |  |  |  |  | 0¦ywnigv: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-88 | AALV-61 Create Confirmation Page | Sub-task | Closed | Major | Fixed | Bhupinder Singh Saini | Richard Van Wyk | Richard Van Wyk | 2016-08-27 12:07 | 2016-09-20 09:36 | 2016-09-20 09:36 | 2016-09-20 09:36 |  |  |  |  | 0 | 2 |  | 0 | 0 |  | 0% |  |  |  | Create and integrate into existing app a good confirmation page. |  | 0% | 0% |  | 0 | 0 |  |  |  |  | 0¦ywnign: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-87 | AALV-61 Create Service to process data | Sub-task | Closed | Major | Fixed | Anneke Kotze | Richard Van Wyk | Richard Van Wyk | 2016-08-27 12:07 |  | 2016-09-16 14:58 | 2016-09-16 14:58 |  |  |  |  | 0 | 1 |  | 14400 | 0 | 21600 | 150% | [5 empty] | 100% | 100% | 21600 | 0 | 14400 |  |  |  |  | 0¦ywnigf: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-86 | AALV-61 Create acceptance form page for teachers | Sub-task | Resolved | Major | Fixed | Sara Abdulrahman M Alraddadi | Richard Van Wyk | Richard Van Wyk | 2016-08-27 12:06 |  | 2016-09-10 18:04 | 2016-09-10 18:04 |  |  |  |  | 0 | 1 |  | 10800 | 0 | 3600 | 33% | [5 empty] | 100% | 100% | 3600 | 0 | 10800 |  |  |  |  | 0¦ywnig7: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-85 | AALV-61 Create DB Queries | Sub-task | Closed | Major | Fixed | Brendan Rothwell | Richard Van Wyk | Richard Van Wyk | 2016-08-27 12:06 |  | 2016-09-04 17:35 | 2016-09-04 17:35 |  |  |  |  | 0 | 1 |  | 3600 | 0 | 7200 | 200% | [5 empty] | 100% | 100% | 7200 | 0 | 3600 |  |  |  |  | 0¦ywnifz: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-84 | AALV-11 Test Student lesson applications | Sub-task | Resolved | Major | Fixed | Brenton Buchbach | Richard Van Wyk | Richard Van Wyk | 2016-08-27 12:06 |  | 2016-09-06 20:55 | 2016-09-06 20:55 |  |  |  |  | 0 | 1 |  | 7200 | 0 | 7200 | 100% | [5 empty] | 100% | 100% | 7200 | 0 | 7200 |  |  |  |  | 0¦ywnifr: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-83 | AALV-11 Create Confirmation Page & Send Notification | Sub-task | Resolved | Major | Fixed | Sara Abdulrahman M Alraddadi | Richard Van Wyk | Richard Van Wyk | 2016-08-27 12:05 |  | 2016-09-08 02:08 | 2016-09-08 02:08 |  |  |  |  | 0 | 1 |  | 3600 | 1800 | 1800 | 50% | [5 empty] | 50% | 50% | 1800 | 1800 | 3600 |  |  |  |  | 0¦ywnifj: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-82 | AALV-11 Create Service(s) for application processing | Sub-task | Resolved | Major | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-08-27 12:05 |  | 2016-09-16 20:08 | 2016-09-16 20:08 |  |  |  |  | 0 | 1 |  | 10800 | 0 | 10800 | 100% | [5 empty] | 100% | 100% | 10800 | 0 | 10800 |  |  |  |  | 0¦ywnifb: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-81 | AALV-11 Create Lesson Application page | Sub-task | Resolved | Major | Done | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-27 12:04 | 2016-10-11 14:25 | 2016-10-11 14:25 | 2016-09-06 20:55 |  |  |  |  | 0 | 1 |  | 14400 | 3600 | 10800 | 75% | [5 empty] | 75% | 75% | 10800 | 3600 | 14400 |  |  |  |  | 0¦ywnif3: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-80 | AALV-11 Create DB table(s) and Queries | Sub-task | Closed | Major | Fixed | Brendan Rothwell | Richard Van Wyk | Richard Van Wyk | 2016-08-27 12:03 |  | 2016-09-04 17:35 | 2016-09-04 17:35 |  |  |  |  | 0 | 1 |  | 7200 | 0 | 7200 | 100% | [5 empty] | 100% | 100% | 7200 | 0 | 7200 |  |  |  |  | 0¦ywniev: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-79 | AALV-27 Test creation of Teacher Accounts | Sub-task | Closed | Major | Fixed | Brenton Buchbach | Richard Van Wyk | Richard Van Wyk | 2016-08-27 12:00 |  | 2016-09-06 12:51 | 2016-09-05 21:59 |  |  |  |  | 0 | 1 |  | 7200 | 0 | 7200 | 100% | [5 empty] | 100% | 100% | 7200 | 0 | 7200 |  |  |  |  | 0¦ywnien: | Sprint 1
IFB299 2016-Sem2 055 | AALV-78 | AALV-27 Create services for processing data | Sub-task | Closed | Major | Fixed | Anneke Kotze | Richard Van Wyk | Richard Van Wyk | 2016-08-27 11:59 |  | 2016-09-06 12:49 | 2016-09-06 12:49 |  |  |  |  | 0 | 1 |  | 7200 | 0 | 14400 | 200% | [5 empty] | 100% | 100% | 14400 | 0 | 7200 |  |  |  |  | 0¦ywnief: | Sprint 1
IFB299 2016-Sem2 055 | AALV-77 | AALV-27 Form Validation | Sub-task | Closed | Major | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-08-27 11:59 |  | 2016-09-06 12:51 | 2016-09-05 21:59 |  |  |  |  | 0 | 1 |  | 7200 | 0 | 7200 | 100% | [5 empty] | 100% | 100% | 7200 | 0 | 7200 |  |  |  |  | 0¦ywnie7: | Sprint 1
IFB299 2016-Sem2 055 | AALV-76 | AALV-27 Create detail entry forms | Sub-task | Closed | Major | Done | Sara Abdulrahman M Alraddadi | Richard Van Wyk | Richard Van Wyk | 2016-08-27 11:59 |  | 2016-09-06 12:51 | 2016-09-01 09:49 |  |  |  |  | 0 | 2 |  | 14400 | 0 | 25200 | 175% | [5 empty] | 100% | 100% | 25200 | 0 | 14400 |  |  |  |  | 0¦ywnidz: | Sprint 1
IFB299 2016-Sem2 055 | AALV-75 | AALV-27 Create DB table(s) and Queries | Sub-task | Closed | Major | Fixed | Aditya Raja | Richard Van Wyk | Richard Van Wyk | 2016-08-27 11:58 |  | 2016-09-04 17:34 | 2016-09-04 17:34 |  |  |  |  | 0 | 1 |  | 7200 | 0 | 7200 | 100% | [5 empty] | 100% | 100% | 7200 | 0 | 7200 |  |  |  |  | 0¦ywnidr: | Sprint 1
IFB299 2016-Sem2 055 | AALV-74 | AALV-60 Test Student Registration | Sub-task | Resolved | Major | Done | Brenton Buchbach | Richard Van Wyk | Richard Van Wyk | 2016-08-27 11:56 |  | 2016-09-05 21:58 | 2016-09-05 21:58 |  |  |  |  | 0 | 1 |  | 7200 | 0 | 7200 | 100% | [5 empty] | 100% | 100% | 7200 | 0 | 7200 |  |  |  |  | 0¦ywnidj: | Sprint 1
IFB299 2016-Sem2 055 | AALV-73 | AALV-60 Create Service(s) for validation and registration | Sub-task | Closed | Major | Done | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-08-27 11:54 |  | 2016-09-05 21:57 | 2016-09-05 21:57 |  |  |  |  | 0 | 1 |  | 14400 | 0 | 14400 | 100% | [5 empty] | 100% | 100% | 14400 | 0 | 14400 |  |  |  |  | 0¦ywnidb: | Sprint 1
IFB299 2016-Sem2 055 | AALV-72 | AALV-60 Registration Form Validation | Sub-task | Closed | Major | Fixed | Anneke Kotze | Richard Van Wyk | Richard Van Wyk | 2016-08-27 11:52 |  | 2016-09-04 20:52 | 2016-09-04 20:51 |  |  |  |  | 0 | 1 |  | 7200 | 0 | 10800 | 150% | [5 empty] | 100% | 100% | 10800 | 0 | 7200 |  |  |  |  | 0¦ywnid3: | Sprint 1
IFB299 2016-Sem2 055 | AALV-71 | AALV-60 Create Registration Page for students | Sub-task | Resolved | Major | Fixed | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-27 11:51 | 2016-10-11 14:25 | 2016-10-11 14:25 | 2016-09-05 21:58 |  |  |  |  | 0 | 1 |  | 14400 | 0 | 14400 | 100% | [5 empty] | 100% | 100% | 14400 | 0 | 14400 |  |  |  |  | 0¦ywnicv: | Sprint 1
IFB299 2016-Sem2 055 | AALV-70 | AALV-60 Create DB table(s) and Queries | Sub-task | Closed | Major | Fixed | Brendan Rothwell | Richard Van Wyk | Richard Van Wyk | 2016-08-27 11:50 |  | 2016-09-04 17:34 | 2016-09-04 17:34 |  |  |  |  | 0 | 1 |  | 7200 | 0 | 7200 | 100% | [5 empty] | 100% | 100% | 7200 | 0 | 7200 |  |  |  |  | 0¦ywnicn: | Sprint 1
IFB299 2016-Sem2 055 | AALV-69 | Create DB table(s) and Queries | Task | Closed | Major | Won't Fix | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-08-27 11:49 |  | 2016-09-08 11:26 | 2016-09-08 11:26 |  |  |  |  | 0 | 1 |  | 120 | 120 |  | 0% | [5 empty] | 0% | 0% |  | 120 | 120 |  |  |  |  | 0¦0000mf:
IFB299 2016-Sem2 055 | AALV-68 | Student - Instrument Waiting List | Story | Open | Should Have | Unresolved | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-22 13:51 |  | 2016-08-25 15:13 | [5 empty] | 0 | 1 | [8 empty] | As a student, I want to apply to be on a waiting list for a instrument so that I can make sure I get an instrument to hire as soon as possible. * Able to join the waiting list for an instrument * Get notified once assigned * Notifies managers about student on waiting list + instrument required * Assigns the student a "waiting list" lesson to show up in schedule view. * Able to cancel waiting * Able to set timeout * Able to change to BYO to start lesson * If teacher gets booked, student is notified | [10 empty] | 0¦ywnezz:
IFB299 2016-Sem2 055 | AALV-67 | Parent - Manage Children's accounts | Story | Open | Should Have | Unresolved | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-20 12:00 |  | 2016-08-25 15:17 | [5 empty] | 0 | 1 | [8 empty] | As a parent, I want to have access to my child’s account, so that I can manage their account for them. * Able to select a child whose account you want to access * Don’t have access to anyone but children * Able to book lessons * Able to view information * Able to view schedule * Able to view borrowed equipment | [10 empty] | 0¦ywnczj:
IFB299 2016-Sem2 055 | AALV-66 | Parent - Bind child | Story | Open | Should Have | Unresolved | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-20 11:59 |  | 2016-08-25 15:17 | [5 empty] | 0 | 1 | [8 empty] | As a parent, I want to add children to my account so that I will have access to them. * Able to search children and add a child account to the parent account * Unable to bind to a child account that already has a parent * Email confirmation sent to child unless the parent account was set up during account creation * Able to bind parent account on account creation or make new parent account on account creation | [10 empty] | 0¦ywnczb:
IFB299 2016-Sem2 055 | AALV-65 | Manager - advanced search teacher applicants | Story | Closed | Could Have | Duplicate | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-18 11:24 |  | 2016-10-06 15:12 | 2016-10-06 15:12 |  |  |  |  | 0 | 1 | [8 empty] | As a manager, I want to conduct an advanced search that included deleted teacher applicants so that I have a larger list of applicants to choose from for a job. * Previously Deleted applicants show up * Non Deleted applicants show up * Hired applicants should disappear * Other filters should still work | [10 empty] | 0¦ywn62m:
IFB299 2016-Sem2 055 | AALV-64 | Manager - informed of empty stock | Story | Open | Should Have | Unresolved | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-18 11:18 |  | 2016-08-25 15:13 | [5 empty] | 0 | 1 | [8 empty] | As a manager, I want to be informed when a specific instrument stock runs out so that I can buy more. * When stock runs out (a student hired the last of a specific instrument), the manager is notified. * Manager isn't notified too late. | [10 empty] | 0¦ywnby7:
IFB299 2016-Sem2 055 | AALV-63 | Manager - enable teacher account | Story | Resolved | Could Have | Fixed | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-18 11:17 |  | 2016-10-23 19:18 | 2016-10-23 19:18 |  |  |  |  | 0 | 1 | [5 empty] | AALV-213, AALV-214, AALV-215 |  |  | As a Manager, I want to re-enable a teacher account of a teacher that has left so that I can rehire previous staff. |  |  | 28% | 5100 | 12900 | 18000 |  |  |  |  | 0¦ywn62l: | Sprint 4
IFB299 2016-Sem2 055 | AALV-62 | Student - Apply for waiting list | Story | Open | Could Have | Unresolved | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-18 11:15 |  | 2016-08-25 15:17 | [5 empty] | 0 | 1 | [8 empty] | As a student, I want to apply to be on a waiting list for a specific time slot so that I can get the lesson I want. * Able to join the waiting list for a specific time * Get notified once assigned * Notifies managers about student in waiting list * Assigns the student a "waiting list" lesson to show up in schedule view. * Able to cancel waiting * Able to set timeout | [10 empty] | 0¦ywnbxr:
IFB299 2016-Sem2 055 | AALV-61 | Teacher - Accept Student | Story | Resolved | Must Have | Fixed | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-18 11:11 | 2016-09-21 21:44 | 2016-09-21 21:44 | 2016-09-21 21:44 | V1 | V1 |  |  | 0 | 1 | [5 empty] | AALV-85, AALV-86, AALV-87, AALV-88, AALV-89, AALV-121, AALV-138, AALV-147 |  |  | As a Teacher, I want to accept a student so that I can teach them. * Able to view students who want to be taught by the teacher. * Able to accept the student * If accepted, time gets booked in teacher + student's schedules * Student and Management gets notified * Able to decline the student (with reason) * if declined, student is informed if they specifically requested the teacher * if declined, management is informed and sent the reason * teach request gets sent to another teacher. |  |  | 100% | 47400 | 0 | 48600 |  |  |  |  | 0¦0000lj: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-60 | Student - Register | Story | Resolved | Must Have | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-08-15 12:44 |  | 2016-09-19 16:31 | 2016-09-05 21:58 | V1 | V1 |  |  | 0 | 1 |  | 0 | 0 | 0 | 0% | AALV-70, AALV-71, AALV-72, AALV-73, AALV-74 |  |  | As a Student, I want to register to the music school so that I can attend classes there. * Create account * Enter personal details (name, dob, address) * Able to successfully register * Email validation |  |  | 100% | 54000 | 0 | 50400 |  |  |  |  | 0¦ywn9f3: | Sprint 1
IFB299 2016-Sem2 055 | AALV-59 | Student - Borrowed Info | Story | Resolved | Must Have | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-08-15 11:24 | 2016-09-21 21:46 | 2016-09-21 21:46 | 2016-09-21 21:46 | V1 | V1 |  |  | 0 | 1 | [5 empty] | AALV-130, AALV-131, AALV-132, AALV-133 |  |  | As a Student, I want to see what equipment I have hired so that I know what I have. * Lists all equipment borrowed by the student * Does not show anything else * Lists accurate due dates for borrowed equipment |  |  | 58% | 19980 | 14220 | 34200 |  |  |  |  | 0¦ywn9fx:i | Sprint 2
IFB299 2016-Sem2 055 | AALV-58 | Student - Lesson Information | Story | Resolved | Should Have | Fixed | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-15 11:24 | 2016-09-19 16:21 | 2016-09-19 16:31 | 2016-09-19 16:21 | V1 | V1 |  |  | 0 | 1 | [5 empty] | AALV-90, AALV-94, AALV-118, AALV-123, AALV-141 |  |  | As a Student, I want to see what lessons are being offered at the school so that I can decide what I want to learn. * List of instruments taught at school * Amount of spaces available for each instrument * Times of lessons * Teachers available |  |  | 73% | 29220 | 10380 | 28800 |  |  |  |  | 0¦ywn9fx: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-56 | Teacher - Change Student's Experience | Story | Open | Could Have | Unresolved | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-15 11:11 |  | 2016-10-16 17:20 | [5 empty] | 0 | 1 | [8 empty] | As a Teacher, I want to change a student's experience with an instrument so that their experience is properly documented. * Able to update a student's experience via timetable lesson select * Only able to update experience for instrument being taught * Only able to update experience for students being taught * Changes display on relevant pages | [10 empty] | 0¦ywn63t:
IFB299 2016-Sem2 055 | AALV-55 | Student - Request other teacher | Story | Open | Could Have | Unresolved | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-15 11:10 |  | 2016-08-25 15:17 | [5 empty] | 0 | 1 | [8 empty] | As a student, I want to change teachers so that I can have a teacher that satisfies my needs better. * Able to make urgent, ie cancel all future lessons * If urgent, future lessons are cancelled * Able to Request to change teacher * Submit notes on reasons of change * Confirmed by admin and new teacher * Managers notified of request * Email confirmation sent to student * Old teacher is informed | [10 empty] | 0¦ywn8n3:
IFB299 2016-Sem2 055 | AALV-54 | Manager - Change Student's Teacher | Story | Open | Could Have | Unresolved | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-15 11:09 |  | 2016-08-25 15:17 | [5 empty] | 0 | 1 | [8 empty] | As a manager, I want to change the teacher assigned to a student so that I can fulfil student transfer requests. * Change teachers of students * Student and teacher timetables changed to reflect transfer | [10 empty] | 0¦ywn8mn:
IFB299 2016-Sem2 055 | AALV-53 | Teacher - Cancel Student | Story | Open | Could Have | Unresolved | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-15 11:08 |  | 2016-08-25 15:17 | [5 empty] | 0 | 1 | [8 empty] | As a teacher, I want to request a student transfer so that I can stop teaching a student I'm no longer comfortable with. * Able to make urgent, ie cancel all future lessons * If urgent, future lessons are cancelled * Able to select a student to cancel from students taught * Reason for transfer * Managers notified of request * Email confirmation sent to student | [10 empty] | 0¦ywn8m7:
IFB299 2016-Sem2 055 | AALV-52 | Student - Return instrument | Story | Closed | Won't Have | Duplicate | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-15 11:07 |  | 2016-10-06 15:08 | 2016-10-06 15:08 |  |  |  |  | 0 | 1 | [8 empty] | As a student, I want to mark an instrument as returned so that I am no longer liable for it. * Hired out instruments listed * Able to be marked as returned * Confirmation done by managers | [10 empty] | 0¦ywn8lr:
IFB299 2016-Sem2 055 | AALV-51 | Student - Cancel lesson | Story | Closed | Could Have | Fixed | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-15 11:05 | 2016-10-18 11:36 | 2016-10-23 13:08 | 2016-10-23 13:08 |  |  |  |  | 0 | 1 | [5 empty] | AALV-174, AALV-175, AALV-176, AALV-177 | AALV-200, AALV-13 |  | As a student, I want to cancel a lesson so that I do not have to attend. * Future lessons listed * Able to Cancel selected lesson(s) * Email confirmation sent to student and teacher |  |  | 18% | 5700 | 24900 | 30600 |  |  |  |  | 0¦0000gl:2 | Sprint 4
IFB299 2016-Sem2 055 | AALV-50 | Manager - Edit Pages | Story | Open | Won't Have | Unresolved | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-15 11:03 |  | 2016-08-25 15:13 | [5 empty] | 0 | 1 | [8 empty] | As a manager, I want to edit any content on the site so that everything is up to date. * Able to perform Create, Read, Update, Delete operations on all parts of website through an interface. | [10 empty] | 0¦ywn8l3:
IFB299 2016-Sem2 055 | AALV-49 | User - Update Details | Story | Open | Should Have | Unresolved | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-08-15 11:01 | 2016-10-18 22:00 | 2016-10-18 22:00 | [5 empty] | 0 | 1 | [5 empty] | AALV-166, AALV-167, AALV-168, AALV-169 |  |  | As a User, I want to update my details so that my account is up to date. * Able to change personal Info and save it. * If a teacher, able to change languages spoken, instruments and skill levels. * Changes show up in relevant lists |  |  | 61% | 23400 | 14400 | 37800 |  |  |  |  | 0¦ywn5xz: | Sprint 4
IFB299 2016-Sem2 055 | AALV-48 | Teacher Applicant - Get Information | Story | Open | Could Have | Unresolved | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-15 10:59 |  | 2016-10-16 17:27 | [5 empty] | 0 | 1 | [5 empty] | AALV-178, AALV-179, AALV-180, AALV-181 |  |  | As a Teacher Applicant, I want to get information about teacher benefits, rate of pay and employment so that I can compare this job with others. * Page shows approximate rate of pay based on experience * Other benefits shown * Link to applying |  |  | 0% |  | 23400 | 23400 |  |  |  |  | 0¦ywn62r:
IFB299 2016-Sem2 055 | AALV-37 | Manager - Add New Instruments | Story | Resolved | Must Have | Fixed | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:38 | 2016-09-19 16:38 | 2016-09-19 16:38 | 2016-09-19 16:38 | V1 | V1 |  |  | 0 | 1 | [5 empty] | AALV-95, AALV-96, AALV-97, AALV-98, AALV-99 |  |  | As a manager, I want to add new instruments so that they can be viewed and hired. * Add new instruments * Type, condition * Each instrument should have a unique code * New instruments should show up on view |  |  | 80% | 28860 | 7200 | 43200 |  |  |  |  | 0¦ywn9fy: | Sprint 1
IFB299 2016-Sem2 055 | AALV-36 | Manager - Edit Instrument Details | Story | Open | Should Have | Unresolved | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:38 |  | 2016-10-20 14:40 | [5 empty] | 0 | 1 | [5 empty] | AALV-207, AALV-208 |  |  | As a manager, I want to edit instrument details so that I can keep track of instruments more effectively. * Change condition * Change description/notes * Changes should display in relevant lists |  |  | 50% | 7200 | 7200 | 14400 |  |  |  |  | 0¦ywn62h: | Sprint 4
IFB299 2016-Sem2 055 | AALV-35 | Manager - Mark Instruments as Returned | Story | Resolved | Must Have | Fixed | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:38 | 2016-09-21 21:44 | 2016-09-21 21:44 | 2016-09-21 21:44 | V1 | V1 |  |  | 0 | 1 | [5 empty] | AALV-105, AALV-106, AALV-107, AALV-108, AALV-139 |  |  | As a manager, I want to mark instruments as returned so that it can be tracked and rehired. * Shows hired out instruments list * Various filters (by date out, by due date, type) default ID * Can mark as returned * Returned instruments show up in the available instrument view * Notify the student that it has been processed |  |  | 87% | 38280 | 5400 | 30600 |  |  |  |  | 0¦0000lp: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-33 | Manager - View and Filter Instrument List | Story | Resolved | Should Have | Fixed | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:38 |  | 2016-10-23 19:18 | 2016-10-23 19:18 |  |  |  |  | 0 | 2 | [5 empty] | AALV-205, AALV-206, AALV-216 |  |  | As a manager, I want to view and filter the instrument list so that I can find an instrument to edit. * Various filters (type, condition etc) * Shows information: Instrument, ID, Condition, previous hirees * Link to edit page |  |  | 70% | 12600 | 5400 | 16200 |  |  |  |  | 0¦ywn62c: | Sprint 4
IFB299 2016-Sem2 055 | AALV-32 | Manager - View Instrument Hire Requests | Story | Resolved | Must Have | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:37 | 2016-09-21 21:45 | 2016-09-21 21:45 | 2016-09-21 21:45 | V1 | V1 |  |  | 0 | 1 | [5 empty] | AALV-109, AALV-110, AALV-111, AALV-112, AALV-140 |  |  | As a manager, I want to view instrument hire requests so that I can assign a student with an instrument. * Various filters (newest request, student asking, type) * Ability to accept or deny requests * If denied, must give reason * Ability to specify an instrument to give the student or assign randomly. * Student is informed * Once instrument is assigned to a student, it must be marked as hired |  |  | 50% | 17850 | 17850 | 45000 |  |  |  |  | 0¦0000lq: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-31 | Manager - Generate Contracts for Teachers and Students | Story | Open | Should Have | Unresolved | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:37 |  | 2016-10-16 17:21 | [5 empty] | 0 | 1 | [8 empty] | As a manager, I want to generate teacher-student and teacher-business contracts so that the business has the required legal work for employees and clients. * Teacher selected * Student selected * Contracts can be shown on web page, downloaded to computer or sent via email to teachers and students * Contract is valid | [10 empty] | 0¦ywn62v:
IFB299 2016-Sem2 055 | AALV-30 | Manager - Generate Business and IT Reports | Story | Open | Should Have | Unresolved | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:37 |  | 2016-10-24 21:35 | [5 empty] | 0 | 1 | [5 empty] | AALV-209, AALV-210, AALV-211, AALV-212 |  |  | As a manager, I want to generate business and IT reports so that I can analyse various aspects of the business and website. * Reports to be show on web page since dynamic * Specify type of report * It should be accurate |  |  | 86% | 29700 | 4500 | 30600 |  |  |  |  | 0¦ywn61h: | Sprint 4
IFB299 2016-Sem2 055 | AALV-29 | Manager - Deactivate Old Accounts | Story | Resolved | Must Have | Fixed | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:37 | 2016-09-21 21:47 | 2016-09-21 21:47 | 2016-09-21 21:47 | V1 | V1 |  |  | 0 | 1 | [5 empty] | AALV-142, AALV-143, AALV-144, AALV-145 |  |  | As a manager, I want to deactivate old accounts so that fired/retired teachers no longer have access to sensitive content. * View every active teacher account * Ability to delete account * Unable to log into an account that is disabled. |  |  | 68% | 30900 | 14100 | 37800 |  |  |  |  | 0¦ywn9fx:v | Sprint 2
IFB299 2016-Sem2 055 | AALV-28 | Manager - Modify User Group Access | Story | Open | Won't Have | Unresolved | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:37 |  | 2016-08-25 15:13 | [5 empty] | 0 | 1 | [8 empty] | As a manager, I want to modify access of a user group so that I can control who can see what on the website. * Manager can reach a form to change access privileges * Users in modified group have correct access | [10 empty] | 0¦ywn68f:
IFB299 2016-Sem2 055 | AALV-27 | Manager - Create Teacher Accounts | Story | Resolved | Must Have | Fixed | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:37 |  | 2016-09-19 16:31 | 2016-09-08 11:03 | V1 | V1 |  |  | 0 | 1 |  | 0 | 0 | 0 | 0% | AALV-75, AALV-76, AALV-77, AALV-78, AALV-79 |  |  | As a manager, I want to create teacher accounts so that new teachers can have access to the system. * Able to enter general details - Name, email, phone, address * Able to create account if details are given * produces error if not * Email account details to teacher with temp password that needs to be changed on first login * Teacher account can log in after creation * Teacher prompted to change password on login |  |  | 100% | 61200 | 0 | 43200 |  |  |  |  | 0¦ywn9fj: | Sprint 1
IFB299 2016-Sem2 055 | AALV-26 | Manager - Delete Teacher Applicants | Story | Closed | Could Have | Duplicate | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:36 |  | 2016-10-06 15:17 | 2016-10-06 15:17 |  |  |  |  | 0 | 1 | [8 empty] | As a manager, I want to delete applicants so that I will only see relevant applicants. * Hide or delete applicants * Hidden applicants do not show up on main search * Updates application status to "declined until further notice" | [10 empty] | 0¦ywn647:
IFB299 2016-Sem2 055 | AALV-25 | Manager - Repond to Teacher Applicants | Story | Resolved | Should Have | Fixed | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:36 |  | 2016-10-24 17:42 | 2016-10-24 17:42 |  |  |  |  | 0 | 1 | [5 empty] | AALV-191, AALV-192 | AALV-24 |  | As a manager, I want to respond to teacher applicants so that I can mark them as possible candidates. * able to shortlist an applicant * on shortlist, marks them as shortlisted for filtering purposes * on shortlist, emails applicant to notify of shortlisting As a manager, I want to delete applicants so that I will only see relevant applicants. * Hide or delete applicants * Hidden applicants do not show up on main search * Emails applicant to notify them that they have not been selected at this time |  |  | 56% | 8160 | 6240 | 14400 |  |  |  |  | 0¦0000gl:0r | Sprint 4
IFB299 2016-Sem2 055 | AALV-24 | Manager - View and Filter Teacher Applicants | Story | Resolved | Should Have | Fixed | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:36 |  | 2016-10-24 17:42 | 2016-10-24 17:42 |  |  |  |  | 0 | 1 | [5 empty] | AALV-186, AALV-188, AALV-189 | AALV-25, AALV-1 |  | As a manager, I want to view and filter teacher applicants so that I can find a teacher to respond to that fulfils my requirements. * Filters (name, type of instruments known, languages) * Hides inactive/previously deleted applicants * can view an applicant As a manager, I want to conduct an advanced search that included deleted teacher applicants so that I have a larger list of applicants to choose from for a job. * Previously Deleted applicants show up * Non Deleted applicants show up * Hired applicants should disappear * Other filters should still work |  |  | 86% | 25680 | 4020 | 23400 |  |  |  |  | 0¦0000gl:0i | Sprint 4
IFB299 2016-Sem2 055 | AALV-21 | Parent - Pay Fees Online | Story | Open | Could Have | Unresolved | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:36 |  | 2016-08-25 15:13 | [5 empty] | 0 | 1 | [8 empty] | As a parent I want to pay fees online so that I don't have to go through the hassle of bringing cash or sending cash with my child. * Fees page shows outstanding fees and due date * Ability to pay via direct debit/credit/debit card * Confirmation email (tax invoice) * Payment goes through | [10 empty] | 0¦ywn66v:
IFB299 2016-Sem2 055 | AALV-16 | Student - Arrange Teacher Meeting | Story | Open | Could Have | Unresolved | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:36 |  | 2016-08-25 15:17 | [5 empty] | 0 | 1 | [8 empty] | As a student I want to arrange a meeting with a teacher so that I could discuss my position and development so far. * Request meeting * Timetable of possible meeting times shown * Able to add reason for meeting * Confirmation done by teacher * Room and time confirmation sent to email | [10 empty] | 0¦ywn65r:
IFB299 2016-Sem2 055 | AALV-15 | Student - View Instrument History | Story | Resolved | Should Have | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:36 | 2016-09-21 21:47 | 2016-09-21 21:47 | 2016-09-21 21:47 | V1 | V1 |  |  | 0 | 1 |  |  | 0 | 300 |  | AALV-134, AALV-135, AALV-136, AALV-137 |  |  | As a student I want to view my instrument history so that I can rehire an instrument I’m used to. * Only shows instruments previously hired/currently being hired. * Shows name, ID, type and condition |  | 100% | 37% | 12300 | 20400 | 34200 |  |  |  |  | 0¦ywn9fx:r | Sprint 2
IFB299 2016-Sem2 055 | AALV-14 | Student - Hire Instrument | Story | Resolved | Must Have | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:35 | 2016-09-21 21:44 | 2016-09-21 21:44 | 2016-09-21 21:44 | V1 | V1 |  |  | 0 | 1 | [5 empty] | AALV-100, AALV-101, AALV-102, AALV-103, AALV-104 |  |  | As a student I want to hire an instrument from the school so that I have an instrument for my lesson. * Instrument Filtering for a specific instrument * Can't request a borrowed or broken instrument * Must specify length of time * Must specify payment method * Once requested, other students are unable to put in a request for the same instrument. |  |  | 83% | 56220 | 10800 | 57600 |  |  |  |  | 0¦0000ln: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-13 | Student - View Lessons | Story | Closed | Must Have | Fixed | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:35 |  | 2016-10-23 13:10 | 2016-10-23 13:10 |  |  |  |  | 0 | 1 | [5 empty] | AALV-158, AALV-159, AALV-160, AALV-161 | AALV-51 |  | As a student I want to view my lessons and lesson details so that I can prepare for my classes. * Able to view my booked lessons * Able to see any lessons that haven't been accepted yet * Shows the date, time, location, teacher and instrument * Can’t see anyone else's lessons |  |  | 46% | 7500 | 8700 | 19800 |  |  |  |  | 0¦0000gl:1 | Sprint 4
IFB299 2016-Sem2 055 | AALV-12 | Student - Request Specific Teacher | Story | Closed | Should Have | Fixed | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:35 | 2016-09-21 21:49 | 2016-10-16 17:09 | 2016-10-16 17:09 |  |  |  |  | 0 | 1 | [5 empty] | AALV-113, AALV-114, AALV-115, AALV-117, AALV-122 |  |  | As a student I want to request a specific teacher so that I can be taught be someone I’m more comfortable with. * Assign prefered teacher in the class registration page * Request is considered/sent to that teacher first |  |  | 77% | 45960 | 13440 | 50400 |  |  |  |  | 0¦0000lq:i | Sprint 1, Sprint 3
IFB299 2016-Sem2 055 | AALV-11 | Student - Apply for Lessons | Story | Resolved | Must Have | Fixed | Richard Van Wyk | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:35 |  | 2016-09-19 16:31 | 2016-09-16 20:08 | V1 | V1 |  |  | 0 | 1 | [5 empty] | AALV-80, AALV-81, AALV-82, AALV-83, AALV-84 |  |  | As a student I want to apply for lessons at the school so that I can learn an instrument. * Limited to 1 lesson if new, up to 3 if coming back * Validation on data entered * Either BYO instrument or hire from school (must be one of the two) * Enter approximate instrument experience * Times for lesson * Reuccering? * Payment Method * Instrument * Teacher * Available times |  |  | 87% | 37800 | 5400 | 43200 |  |  |  |  | 0¦ywn9fr: | Sprint 1, Sprint 2
IFB299 2016-Sem2 055 | AALV-10 | Teacher - Add Notes to Student | Story | Open | Could Have | Unresolved | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:35 |  | 2016-10-16 17:20 | [5 empty] | 0 | 1 | [8 empty] | As a teacher I want to add notes to specific students so that I can teach them more effectively. * Can Add notes * Can Delete/edit notes * Can’t view students not taught by that teacher * Notes show up on relevant screens * Notes can be shared with students, in which case they are emailed with it. | [10 empty] | 0¦ywn63v:
IFB299 2016-Sem2 055 | AALV-8 | Teacher - View Report: Lesson Bookings | Story | Open | Could Have | Unresolved | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:35 |  | 2016-08-25 15:17 | [5 empty] | 0 | 1 | [8 empty] | As a teacher I want to view lesson booking reports so that I am informed on what lesson times are in high demand. * Shown as table/timetable * Colour coded (based on demand) * Specific to instruments taught by the teacher * Report generates accurately | [10 empty] | 0¦ywn63z:
IFB299 2016-Sem2 055 | AALV-7 | Teacher - Manage meetings | Story | Open | Could Have | Unresolved | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:35 |  | 2016-08-25 15:17 | [5 empty] | 0 | 1 | [8 empty] | As a teacher I want to view or manage my student/parent meetings so that I can organise them into my schedule. * Shown as table/timetable * Colour coded * Show students/parents name * Start and finish times * Room number * Print friendly * Able to accept or decline meetings * On Accepting, email other party * If declining, option to add another date * On decline, email other party | [10 empty] | 0¦ywn63r:
IFB299 2016-Sem2 055 | AALV-5 | Teacher - View Lessons Booked | Story | Closed | Must Have | Fixed | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:35 |  | 2016-10-16 17:09 | 2016-10-16 17:09 |  |  |  |  | 0 | 1 | [5 empty] | AALV-150, AALV-151, AALV-152, AALV-153 |  |  | As a teacher I want to view my booked lessons at the music school so that I know when I have to be there to teach a lesson. * Able to view own lessons * Can’t view other teachers’ lessons * Information displayed is correct * Shows Time,Student, Room and Instruments |  |  | 82% | 31320 | 6480 | 27000 |  |  |  |  | 0¦0000lv: | Sprint 3
IFB299 2016-Sem2 055 | AALV-4 | Teacher - View Student Info | Story | Closed | Should Have | Duplicate | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:35 |  | 2016-10-06 15:07 | 2016-10-06 15:07 |  |  |  |  | 0 | 1 | [8 empty] | As a teacher I want to view information about my students so that I can prepare for my lessons with them. * Shows name, instruments, previous notes, experience and times. * Does not display additional information * Only available for students taught by the teacher. | [10 empty] | 0¦ywn633:
IFB299 2016-Sem2 055 | AALV-3 | Teacher - Update Personal Details | Story | Closed | Should Have | Duplicate | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:35 |  | 2016-10-06 15:11 | 2016-10-06 15:11 |  |  |  |  | 0 | 1 | [8 empty] | As a teacher I want to update my personal details so that the music school knows where to contact me. * Able to Update contact info (email, phone address) * Changes show under teacher profile * Managers notified of changes | [10 empty] | 0¦ywn60b:
IFB299 2016-Sem2 055 | AALV-2 | Teacher Applicant - Tracking | Story | Open | Could Have | Unresolved | Unassigned | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:35 |  | 2016-08-25 15:13 | [5 empty] | 0 | 1 | [8 empty] | As a teacher applicant I want to track the status of my application so that I know whether or not I’m being considered for a job. * Able to enter tracking ID that was emailed on initial contact * Links to page that states status of application * Different notification states (Pending, accepted, declined etc) display correctly * Tracking occurs correctly and accurate information is shown. * can't view someone else's information | [10 empty] | 0¦ywn62n:
IFB299 2016-Sem2 055 | AALV-1 | Teacher Applicant - Apply | Story | Closed | Should Have | Fixed | Anneke Kotze | Richard Van Wyk | Richard Van Wyk | 2016-08-08 08:34 |  | 2016-10-18 08:37 | 2016-10-18 08:37 |  |  |  |  | 0 | 2 |  |  | 0 | 600 |  | AALV-182, AALV-184, AALV-185 | AALV-24 |  | As a teacher applicant I want to apply for a position at the school so that I can be considered for a job. * Upload resume (see comment below list) * List Instruments played and your skill in them * Input Contact information (Name, Email, Phone number, address) * Cover letter text box for input * Emails thank you to applicant on submit Cannot do file uploads as it would require us to rewrite half of the site Requirement for resume upload is now changed to simply adding references and selecting a rough hours per week preference |  | 100% | 70% | 16500 | 6900 | 23400 |  |  |  |  | 0¦0000ly:z | Sprint 3
Generated at Tue Oct 25 12:47:13 EST 2016 by Richard Van Wyk using JIRA 6.2.7#6265-sha1:91604a8de81892a3e362e0afee505432f29579b0.