## Slide 1
Data55:
Richard, Anneke, Brendan,
Sara, Brenton, Saini and Aditya

## Slide 2: Overview - Framework
AngularJS client side applications
  Means one consistent language between client and server side
Node.js server side handling
  Allows for easier manipulation of HTTP requests
  Allows for development of a RESTful Web service
PostgreSQL (Postgres) database
  Very similar to mySQL
  Known for compatibility with angular and node

## Slide 3: Overview - Stories assigned to Sprint
Student - Registration
Teacher - Registration
Student - Apply for Lessons
Teacher - Accept Student
Student - Get General Lesson Information
Manager - Add New Instruments
Student - Hire Instrument
Manager - Mark Instruments Returned
Manager - View Instrument Hire Requests

## Slide 4: Overview - Stories Status
Untouched | In Progress/Almost Finished | Finished/Testing
 |  | Student Registration
 |  | Teacher Registration
 | Student Lesson Application | 
 | Accept Student | 
 | Lesson Information Page | 
 |  | Add New Instruments
 | Student Hire Instrument | 
Manager Inst. Hire requests |  | 
Student Specific Teacher |  | 

## Slide 5: Overview - Time Management & Issues encountered
New tools and languages
No login user story
Not everyone understands the system architecture yet
Not everyone is familiar with GitHub
Misunderstandings of user story (Get Lesson Info)
These issues resulted in additional time being spent on all tasks, as well as existing user stories needing to be delayed for more important ones.

## Slide 6: Overview - Hour Burndown Chart

## Slide 7: Stories: Student Registration (AALV-60)
Done:
Created Database Tables and Queries
Created Frontend Page
Added Validation
Created Service to manage registration
To do:
Email services
Test to ensure no errors or bugs
Merge Template with Application

## Slide 8: Stories: Teacher Registration (AALV-27)
Done:
Created Database Tables and Queries
Created Frontend Page
Added Validation
Created Service to manage registration
To do:
Email services
Test to ensure no errors or bugs
Merge Template with Application

## Slide 9: Stories: Student Lesson Application (AALV-11)
Done:
Created Database Tables and Queries
Created Frontend Page
Added Validation
Created Service to manage registration
To do:
Style Confirmation Page
Email services
Test to ensure no errors or bugs
Merge Template with Application

## Slide 10: Stories: Teacher Accept Student (AALV-61)
Done:
Created Database Tables and Queries
Created Frontend Page
To do:
Add Validation
Create Service
Test to ensure no errors or bugs
Merge Template with Application

## Slide 11: Stories: Student Get Lesson Info (AALV-58)
Done:
Created Frontend Page
Wrote Content
To do:
Style Page

## Slide 12: Stories: Add New Instruments (AALV-37)
Done:
Created Database Tables
Created Frontend Page
Add Validation
Create Service
To do:
Testing

## Slide 13: Stories: Hire Instruments (AALV-14)
Done:
Created Database Tables
Created Frontend Page
Created Slot in lesson application
To do:
Create Service
Testing

## Slide 14: Stories: Return Instruments (AALV-35)
Done:
Created Database Tables
To do:
Create Page
Create Service
Testing

## Slide 15: Stories: View Hire Requests (AALV-32)
Done:
Created Database Tables
Create Page
To do:
Create Service
Testing
Acceptance Criteria:
Various filters (newest request, student asking, type)
Ability to accept or deny requests
If denied, must give reason
Ability to specify an instrument to give the student or assign randomly.
Student is informed
Once instrument is assigned to a student, it must be marked as hired

## Slide 16: Stories: Request Specific Teacher (AALV-12)
Done:
Created Database Tables
Create Page
To do:
Create Service
Testing